HAND-OUT N° 07

Session 7: Estimating the budget for laboratories and X-rays

Topics covered in this session

1. Description and explanation of the structure of Laboratory and X-rays worksheet.

2. Explanation of how the quick estimate is done for laboratory inputs, and its limitations.

3. Description of the standard structure used in the tool to plan and budget for microscopy, culture and DST laboratories.

4. Presentation of the list of laboratory items and the estimates of equipment costs, as well as how to change them if needed.

5. Explanation of the different possibilities to budget for equipment and reagents for culture: solid vs. liquid media.

6. How to plan and budget for a full equipment list or only for a few items.

7. Description of the quality assurance and laboratory training components of the worksheet.

Exercise

Some data have already been entered in this worksheet. To complete the worksheet, the following information is available:

- The programme plans to upgrade and repair 140 microscopy laboratories every two years, starting in 2007. The central unit thinks that the default value for upgrading and repairing a laboratory does not apply to Kenya, and that the cost appropriate in Kenya is US$ 4,286 per laboratory.

- There are no plans to establish any new microscopy laboratories and therefore no need to purchase a full package of equipment for any laboratory. However, there is a need to replace old microscopes. It is estimated that 80 new microscopes will need to be purchased in each year 2006 to 2011. The unit cost of a microscope is US$ 2,400.

- The default value for the cost of one sputum smear is US$ 1 in the tool. However, the Kenyan NTP has estimated that in Kenya the cost is US$ 0.16.

- The NTP plans to establish one new culture laboratory in 2008. The cost for the infrastructure is US$350,000 for a new culture laboratory and the cost for the full package of equipment required in such a laboratory is estimated at US$ 240,000. Two other laboratories already perform cultures and will be renovated during 2007. The cost of this renovation is estimated at US$ 100,000 for each laboratory.

- The cost of transporting culture specimens to the international reference laboratory in Australia for quality assurance purposes is about US$ 4,000 every year. The cost of transporting culture specimens for re-checking samples and panel testing is about US$ 4.5 per culture. About 20% of all samples are re-checked.

- The central government provides financing of US$ 70,000 per year. The programme has mobilized resources from the Global Fund of US$ 800,000 per year for the period 2007–2011. Other donors have committed US$ 500,000 per year in 2008 and 2009.

Using this information, data already entered for you in the tool, and the "detailed" method:

1. What is the budget for microscopy laboratories in 2008 and 2009?

2. What is the total budget for culture laboratories in 2008?

3. What is the total budget for the quality assurance programme in 2007?

4. In which year there is the biggest investment for laboratories? How can this be explained?

5. What is the total budget 2007–2011? What would be the total budget for 2007–2011 if we use the quick estimate option?

6. What is the year with the biggest funding gap? What is the total funding gap for 2008–2011?

Expected outcomes

1. Participants are able to develop a detailed budget for routine laboratory activities and laboratory strengthening as well as make a "quick estimate" of this budget using the tool.

2. Participants are familiar with the standard format used within the tool for planning and budgeting for the infrastructure needed for microscopy, culture and DST laboratories.

3. Participants can plan and budget for the equipment needed for microscopy, culture and DST laboratories, with solid or liquid media.

4. Participants are familiar with the standard structure used within the tool for planning and budgeting for laboratory supplies for the different laboratory tests, including smears, cultures, DST for first-line drugs  and DST for second-line drugs.

5. Participants can plan and budget for the different activities involved in a quality assurance programme.

6. Participants can plan and budget for other diagnostic items necessary for the TB control programme.