## Slide 1: The Roadmap to Successful Xpert Implementation
- 37 steps -

## Slide 2
Phases of Xpert implementation
NTP establishes National
Xpert Working Group
Working Group develops
draft Xpert strategy
Site assessments
Finalize
Xpert Strategy
Preparation
Training & Installation
Monitoring & Evaluation
Scale-up Strategy

## Slide 3
Critical pathway to Xpert implementation

## Slide 4
Phase 1: NTP establishes National Xpert Working Group
Talk with the NTP/ MoH
Mapping of NTP/ partner activities
Set-up Xpert WG
Meeting of the Xpert WG
Convene stakeholders meeting

## Slide 5
Activities | Expected outcomes
Talk with the NTP/MoH Mapping of NTP/partner activities Convene stakeholders meeting Set-up an Xpert working group (important to have representation of program managers and clinicians (TB, pediatricians, HIV) Arrange for an Xpert WG meeting | -Planning & coordination body established - Commitment to start using Xpert ,based on understanding of program and cost implications
Phase 1: NTP establishes National Xpert Working Group

## Slide 6
Agree on eligible suspect groups
Draft diagnostic algorithm
Provide background information on Xpert
Determine objectives of Xpert
Review epidemiology situation
Perform SWOT Analysis of diagnostic/ treatment situation
Develop M&E framework
Preselect potential sites
Phase 2: Working Group develops draft Xpert strategy

## Slide 7
Phase 1: Introduction
Activities | Expected outcomes
Provide background information on Xpert Evaluate epidemiologic situation Perform SWOT analysis of diagnostic and treatment situation Determine objectives for Xpert Agree on eligible suspects Develop a draft algorithm (describing the complete new diagnositic and treatment pathways) Pre-select potential sites for Xpert placement Draft an M&E framework | -A draft national Xpert strategy, national algorithms and SOP’s have been developed - Commitment of all partners and professional groups to use the national algorithms
Phase 2: Working Group develops draft Xpert strategy

## Slide 8
Phase 2: Strategic Planning
Collect estimated number of suspects per site
Assess treatment capacity
Phase 3: Site Assessments
Asses HR requirements
Assess requirements for laboratory renovation
Phase 3: Site Assessments

## Slide 9
Phase 1: Introduction
Activities | Expected outcomes
Collect data on estimated number of suspects from sites Idenfity effectiveness of patient/sample referral network Identify training needs at sites Identify requirements for laboratory renovation & staffing Assess treatment quality and capacity | -Essential information for finalizing the national strategy, algorithms and development of an activity plan have been collected
Phase 3: Site Assessments

## Slide 10
Finalize M&E Plan
Select final sites for Xpert placement
Finalize diagnostic algorithms & suspect selection
Develop annual activity plan
Develop budget
Phase 4: Finalize Xpert strategy

## Slide 11
Phase 1: Introduction
Activities | Expected outcomes
Select final sites for Xpert placement & prioritization for phased implementation Finalize diagnostic & suspect selection Develop M&E plan Develop an annual activity plan Forecast Xpert supplies and drug needs Develop a budget | -National Xpert strategy has been finalized, including an annual activity plan and budget
Phase 4: Finalize Xpert strategy

## Slide 12
Establish waste management system
Establish Xpert maintenance system
Establish cartridge supply system
Revise registers & request forms
Develop clinical protocols
Develop SOPs
Conduct lab renovations
Establish supervision system
Finalize procurement
Phase 5: Preparation

## Slide 13
Phase 1: Introduction
Activities | Expected outcomes
Conduct laboratory renovations Develop clinical protocols Revise registers & request forms Develop site reporting template (M&E) Develop SOPs Develop training plan Develop a supervision plan Finalize procurement Set-up a cartridge supply system Develop a maintenance plan Develop waste-management plan | Lab renovations completed, documents and lab support systems (maintenance, supervision etc) developed
Phase 5: Preparation

## Slide 14
Conduct Training of trainers
Conduct site specific training
Install GeneXpert instruments
Phase 6: Training & Installation

## Slide 15
Phase 1: Introduction
Activities | Expected outcomes
Conduct training of trainers (ToT) Conduct site-specific trainings of laboratory & clinical staff Install the GeneXpert instruments Place revised registers and SOPs in laboratory and clinics | -Routine use of Xpert has started
Phase 6: Training & Installation

## Slide 16
Conduct monitoring & supervision visits
Evaluate the quality & impact of Xpert use
Phase 7: Monitoring & Evaluation

## Slide 17
Activities | Expected outcomes
Conduct monitoring & supervision visits Improve lab operator skills (mentorship) Improve recording & reporting Collect monthly (lab) quality indicators Evalute the quality and impact of Xpert use | -Quality of Xpert routine use is ensured -Benefits and obstacles of Xpert used are evaluated
Phase 7: Monitoring & Evaluation

## Slide 18
Determine perspectives for the future role of Xpert in the country: Final national guideline
Phase 8: Scale up Strategy

## Slide 19
Phase 1: Introduction
Activities | Expected outcomes
Determine perspectives for the future role of Xpert in the country Develop final national guideline | -Finalized national Xpert scale up strategy
Phase 8: Scale up Strategy